## UAT Checklist
Topic | Test | No. | Description | Expected Outcome | Pass/Fail | Comment | Status | Kepion Review
General Functionalities
Login and Security | Login to Kepion | 1 | Log in to Kepion through https://customer.kepion.com/ using account name or email. (You would have received an initial password to your email) | - Be able to log in successfully. - Planning users should be able to see the "Budgeting and Forecasting" app. - Reporting users should be able to see the "Management Reporting" app. - Power users should be able to see two additional apps "Data Management" and "Configuration".
General Functionalities | Start applications | 2 | Double-click each app to open it then browse different reports. | - Be able to view pages of different sections in the menu. - For each page, the form is well presented.
| Form Function | 3 | For each page, test the form functionalities which includes: - Change the filter selections; - Expand/collapse rows with fold-up; - Click the buttons of form bar. | - The form displays the correct dataset as filters change. - The rows are able to be expanded and collapsed. - The actions in the form bar are able to be triggered.
| Exit applications | 4 | Hover over the Action in upper right corner then click "Exit" | App is able to exit with or without saving.
Budgeting and Forecasting App
Reports Section | Data display | 5 | Review the PnL and Variance reports and check the data accuracy when changing filter selections. | Both reports display correct data.
Revenue Section | Revenue data entry | 6 | Enter the testing data in each report. Click "Post" after data entry at each page. | - Data is posted and saved in proper format (Numeric or percentile). - The saved data is calculated and flowed to Sales PnL report.
| Data display | 7 | Review the Sales PnL report and check the data accuracy when changing filter selections. | The report displays correct data with calculations of input.
Opex Section | Opex data entry | 8 | Enter the testing data in Opex Planning and Lineitem Planning reports. Click "Post" after data entry. | Data is posted and saved.
| Data calculation | 9 | Review Opex Planning report. | Data in lineitem planning is aggregated and flowed into the appropriate accounts in the Opex planning report.
Capex Section | Add new asset | 10 | Enter the testing data in Create/Update Asset report. Click "Update" to post the data. | - Asset data is posted and saved. - The Depreciate & Amortization columns display correct calculated numbers.
| Add new row | 11 | Click "Add More Rows" to add one more row in Create/Update Asset report. | New row is added.
| Assumption adjustment | 12 | Enter useful life for different asset types in Depr. Assumption report. Click "Update" to post the data. | The useful life data is posted and flowed into calculations.
| Data calculation and display | 13 | Review Capex Overview report. | The Capex overview displays the correct data calculated by the other two reports.
Workforce Section | Add existing employee | 14 | Click "Add Employee" to add the employee's name, department and position in Existing Employees report, then enter the required information for that employee. | - New employee is added. - Be able to input employee assumption information.
| Add new hire | 15 | Click "Add New Hire" to add employee name, department and position in New Hires report. | - New hire is added. - Be able to input new hire assumption information.
| Promote employee | 16 | Select one employee in the filter and click "Promote" to choose their new position and start date in Promote/Transfer report. | Be able to change the position and start date.
| Transfer employee | 17 | Select one employee in the filter and click "Transfer" to choose their new location, department and start date in Promote/Transfer report. | Be able to change the location, department and start date.
| Add assumption level | 18 | Click "Add Level" to add a desired level number to the category in Workforce Assumption report. | Be able to add the level numbers.
| Change level name | 19 | Right-click a level cell of the assumption form, then click "Rename Level" to change the level name in Workforce Assumption report. | Be able to change level names.
| Remove level | 20 | Right-click another level cell, then click "Delete Level" to remove the selected level in Workforce Assumption report. | Be able to remove unwanted levels.
| Data display | 21 | Review the Workforce Summary report. | The report displays correct data with calculations of input.
Other Income and Expense | Other data entry | 22 | Enter testing data in the Other report, then click "Update". | Data is posted and flowed into PnL report.
App Assumption | Assumption display | 23 | Review the current assumptions | Be able to see assumption data.
Management Reporting App
Executive Dashboard | Metrics and graphs display | 24 | Review the Executive Dashboard. | The key metrics and graphs properly display.
Financial Reports | Data display | 25 | Review three financial reports. Change filter selections. | The reports display correct data accordingly with different filter selections.
Variance Report | Data display | 26 | Select base and comparison scenarios. Review the Variance report. | The reports display correct data accordingly with different scenario selections.
Other Reports | Data display | 27 | Review all other reports. Change filter selections. | The reports display correct data accordingly with different filter selections.
App Assumption | Assumption display | 28 | Review the current assumptions | Be able to see assumption data.
Data Management App
Configure Variables | Current month setup | 29 | Choose the current month, then click "Update". | Be able to change the current month.
| Exchange rates entry | 30 | Enter the exchange rate data, then click "Update". | Be able to update the exchange rates.
Load Actuals | Load actual data | 31
| Data display | 32 | Review the Review GL Actuals report. | The data of loaded actuals is completed and correct.
| Assumption setup | 33 | Update the data loading assumptions, then click "Update". | Be able to update the assumptions.
| Map GL accounts | 34 | Select the mapping IS and BS accounts from drop-downs, then click "Update". | Be able to update the mapping accounts. The data of GL accounts is calculated and flowed to IS and BS accounts correctly.
| Clean data | 35 | Click "Clean Business Data" | All data is removed.
Manage Scenarios | Edit description | 36 | Enter/Change the description of different scenarios in the overview report, then select "Action -> Post". | Be able to update description.
| Preseed scenarios | 37 | Configure the preseeding scenarios with dropdowns, then click "Preseed". Review PnL report below. | Be able to set the proper scenarios and fiscal years. Be able to view the PnL report.
| Manage what-if scenarios | 38 | Select to enable or not for different scenarios, then click "Update". Review PnL report below. | Be able to enable/disable what-if scenarios. Be able to view the PnL report.
| Archive Scenario | 39 | Configure the archiving scenario with dropdowns, then click "Archive". | Be able to archive desired scenarios.
| Add Scenario | 40 | Click "Add Scenario", enter the name, then click "Run". Review PnL report below. | Be able to add a new scenario. Be able to view the PnL report.
Configuration App
Set up Location | Edit existing location | 41 | Update the information of existing location, then click "Save". | Be able to update existing location.
| Add new location | 42 | Click "Add New" to add a new location. | Be able to add the new location.
| Remove location | 43 | Choose the dropdown of Action in one location to remove it with or without relevant data. | Be able to remove unwanted locatoin.
Revenue Planning | Add new account | 44 | Click "Add New" to add a new revenue or COGS account. | Be able to add the new account.
| Remove account | 45 | Choose the dropdown of Action in one revenue or COGS account to remove it with or without relevant data. | Be able to remove unwanted account.
| Add dimension | 46 | Click "Add New" to add a new product or customer dimension. | Be able to add a new dimension.
| Edit existing dimension | 47 | Update the information of existing product or customer, then click "Save". | Be able to update existing product or customer.
| Remove dimension | 48 | Choose the dropdown of Action in one product or customer to remove it with or without relevant data. | Be able to remove unwanted product or customer.
Opex Planning | Add new account | 49 | Click "Add New" to add a new Opex account. | Be able to add the new account.
| Remove account | 50 | Choose the dropdown of Action in one Opex account to remove it with or without relevant data. | Be able to remove unwanted account.
| Add dimension | 51 | Click "Add New" to add a new department dimension. | Be able to add a new dimension.
| Edit existing dimension | 52 | Update the information of existing deparment, then click "Save". | Be able to update existing department.
| Remove dimension | 53 | Choose the dropdown of Action in one department to remove it with or without relevant data. | Be able to remove unwanted department.
Workforce Planning | Add new account | 54 | Click "Add New" to add a new workforce account. | Be able to add the new account.
| Remove account | 55 | Choose the dropdown of Action in one workforce account to remove it with or without relevant data. | Be able to remove unwanted account.
| Add dimension | 56 | Click "Add New" to add a new position or employee dimension. | Be able to add a new dimension.
| Edit existing dimension | 57 | Update the information of existing position or employee, then click "Save". | Be able to update existing position or employee.
| Remove dimension | 58 | Choose the dropdown of Action in one position or employee to remove it with or without relevant data. | Be able to remove unwanted position or employee.
Capex Planning | Add new account | 59 | Click "Add New" to add a new Capex account. | Be able to add the new account.
| Remove account | 60 | Choose the dropdown of Action in one Capex account to remove it with or without relevant data. | Be able to remove unwanted account.
| Add new asset type | 61 | Click "Add New" to add a new asset type. | Be able to add the new asset type.
| Edit existing asset type | 62 | Update the name and associate Capex account, then click "Save". | Be able to update the existing Capex account.
| Remove asset type | 63 | Choose the dropdown of Action in one asset type to remove it with or without relevant data. | Be able to remove unwanted asset type.
Other Planning | Add new account | 64 | Click "Add New" to add a new other income and expense or taxes account. | Be able to add the new account.
| Remove account | 65 | Choose the dropdown of Action in one other income and expense or taxes account to remove it with or without relevant data. | Be able to remove unwanted account.
Other Configuration | Data Load | 66 | Configure the datasets to be included in data load, then click "Save". | Be able to set up the data load.
| App Assumptions | 67 | Update the assumptions, then click "Save". | Be able to set up the app assumptions.